## Seguimiento Defectos
|  | INSTITUTO TECNOLÓGICO SUPERIOR ZACATECAS OCCIDENTE |  |  | LABORATORIO DE MICROCONTROLADORES
Historias de usuario y criterios de aceptación
Bitácora de defectos
Nombre del Proyecto: |  | SemaforosMina
No. Defecto | Fecha creación | Responsable | Descripción del defecto | Historia de Usuario | Fase de proceso | Prioridad | estatus | Resolución | Fecha resolución | Status
1 | 2023-02-16 | RAPR | Eleccion de la raspberry: No se tenia clara la raspberry a utilizar. | HU1 | Cerrado | Alto | Cerrado | Se llego al acuerdo en conjunto el equipo de trabajo y la empresa del modelo a utilizar. | 2023-02-16 | New
2 | 2023-03-06 | RAPR | Funcion del semaforo: Establecer las formas de funcionalidad del semaforo. | HU1 | Cerrado | Alto | Cerrado | Se establecio que el semaforo funcionaria de forma manual, automático y por detección de cámara. | 2023-03-06 | Under Review
3 | 2023-04-14 | RAPR | Desarrollo de codigo: Errores al ejecutar el codigo para la forma manual. | HU2 | Cerrado | Alto | Cerrado | Se reviso y corrigio las lineas de codigo nesesarias. | 2023-04-14 | In Progress
4 | 2023-05-15 | RAPR | Diseño del circuito: Error en el diseño del circuito, no se acoplaba a los requerimientos. | HU3 | Cerrado | Alto | Cerrado | Se creó un nuevo diseño mas eficiente. | 2023-05-15 | Completed
5 | 2023-05-17 | RAPR | Ensamblado: Al ensamblar las piezas del semaforo se presentaron errores ya que se desconocia el orden de algunas.. | HU3 | Cerrado | Alto | Cerrado | Se ordenaron las piezas y posteriormente se colocaron en su lugar. | 2023-05-17
6 | 2023-05-19 | RAPR | Tiempos entre cambio de luces: No coincidian los cambios de luces de los semaforos, ya que no ensendian del color adecuado en el tiempo indicado. | HU3 | Cerrado | Alto | Cerrado | Se establecieron tiempos medidos para que las luces cambiaran adecuadamente. | 2023-05-19
7 | 2023-05-22 | RAPR | Funcionamiento: Se presentaban errores al encender los semaforos. | HU4 | Cerrado | Medio | Cerrado | Se corrigieron las fallas mediante un analisis del funcionamiento. | 2023-05-22

## Instrucciones Defectlog
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).